## Cover Page
Document Name: |  | Estimation-Deaglo
Document ID: |  | USA_0430-USA_0430_02-EST-001
Version: |  | 1
Date: |  | 2022-03-25
Modification History
(Kindly remove the modification history of the Template when using this sheet)
Purpose of the Template |  | This template can be used when SMC Estimation
Date | Author |  | Change Description | Version
2022-03-25 | Prasanth |  | MVP 2 - Admin Functionalities | 0.1
May 22,2022 | Rajeesh Kartha |  | Approved and baselined | 1

## Guidelines
Instructions and Guidelines
1 | Define WBS - Identify the scope (use either the activities/deliverables) for the project to define the WBS for your project.
2 | Split the activities/deliverable into task Level
3 | Define the complexity guidelines for the task based on the meaningful parameters (like No. of UI Fields, No. of Transaction, No. of Validation and etc..)
4 | List down the Assumption & Constrains you have considered for the Estimation
5 | List down the technical and delivery related risk which impact on estimation
6 | Identify the internal and external dependencies.
7 | Create the resource loading sheet based on the timeline and estimation agreed with customer.
8 | Create the project plan with identified milestones and dependecines.
9 | Create the project schedule with start and end date for the list of task idenfied in the plan and assign the task to the identified resources.
10 | Baseline the Estimation, Planning and Schdule and get the formal approval.
11 | Re-Estimate the estimation and plan where there is a change in scope.
12 | Get approval and re-baseline the revised estimation, plan and Schedule.

## SMC Defination
SMC Definition - General Guidelines |  |  |  | Complexity Defination (Java)
S.No | Complexity | Effort | Remarks | / Complexity | Simple | Medium | High
1 | Simple | 5 days | Simple UI pages with less than 5 controls and one db operation with webservice either request or response | JSP (View) | Few Data entry and display elements and submit points (< 10) | More data entry, display elements and submit points ( < 20 ) Page breaks, display logic, Simple usage of DHTML | Complex Validations, Complex Formatting, Complex page layout, Complex display logic
2 | Medium | 8 Days | UI Pages with less than 10 simple controls or UI pages with 1 to 2 complex control with webservice either request or response | Servlet (Controller) | 1-2 operations / request. Retrieval and passing of data elements | More operations per request, Session information storing Operations based on servlet session information | Keeping track of processes across pages Request routing based on intermediate operations
3 | Complex | 12 Days | UI pages with greater than 10 simple control or UI pages with more than 2 complex control and webservice with request and response | EJB (Model) Simple Interface (Few | Simple Interface (Few methods and parameters) Simple data access, data logic (no caching) | Multiple data sources Complex data retrieval and up dation logic Caching | Multiple data sources; involves tables and other sources

## Complexity Definition
| Requirement- 10% |  |  |  | Design - 15% |  |  | Coding - 45% | [6 empty] | Testing - 25% |  |  |  |  | Release - 5% |  |  | Total (Hrs)
Complexity | Requirement Gathering | SRS Preparation | SRS Review | SRS Rework | Technical Design Specifications | TDD Review | TDD Rework | View | Business Layer | DAO Layer | Unit Testing | Rework after Unit Testing | Code review | Code Rework | STP / STD Preparation | STD / STP Review & Rework | Functional Testing | Automation Testing | Rework on Testing Comments | Deployment | User Manual | System testing & UAT Support | Total (Hrs) | Total (Days)
| 30% | 50% | 10% | 10% | 80% | 10% | 10% | 25% | 25% | 20% | 10% | 10% | 5% | 5% | 10% | 10% | 30% | 30% | 20% | 20% | 10% | 70%
S | 1.2 | 2 | 0.4 | 0.4 | 4.8 | 0.6 | 0.6 | 4.5 | 4.5 | 3.6 | 1.8 | 1.8 | 0.9 | 0.9 | 1 | 1 | 3 | 3 | 2 | 0.4 | 0.2 | 1.4 | 40 | 5
M | 1.92 | 3.2 | 0.64 | 0.64 | 7.68 | 0.96 | 0.96 | 7.2 | 7.2 | 5.76 | 2.88 | 2.88 | 1.44 | 1.44 | 1.6 | 1.6 | 4.8 | 4.8 | 3.2 | 0.64 | 0.32 | 2.24 | 64 | 8
C | 2.88 | 4.8 | 0.96 | 0.96 | 11.52 | 1.44 | 1.44 | 10.8 | 10.8 | 8.64 | 4.32 | 4.32 | 2.16 | 2.16 | 2.4 | 2.4 | 7.2 | 7.2 | 4.8 | 0.96 | 0.48 | 3.36 | 96 | 12
| Days | 5 | 8 | 12
| Hrs | 40 | 64 | 96
Phase | % | S | M | C
Requirement | 10% | 4 | 6.4 | 9.6
Design | 15% | 6 | 9.6 | 14.4
Coding & Unit Testing | 45% | 18 | 28.8 | 43.2
Testing | 25% | 10 | 16 | 24
Deployment & Release | 5% | 2 | 3.2 | 4.8

## Assumption
Assumption
1 | Estimation will be re-visited when ever there is change in scope or technolgoy
2 | The baseline complexity definition is for an average skilled resource on the technology.
3 | Arechitecture & Framewor, Workspace Environment Setup, Performance testing, Deployment, UAT & Warranty support are estimated for the complete application not at individual screen
4 | The technology considered for estimations are IDE - VS 2019, VS Code Technology - Python,React,.Net , AWS Framework - .Net Application Server - AWS serverless Session Management - React,AWS Cognito Unit Testing - Junit Functional Testing - Manual Coding Standards - Sonar Build / Deployment - AWS Deployment Load / Stress Testing - Manual Version Control - Github PR Tracker - NA
5 | Since MVP is the base for MVP2 and exposure screens are not available in MVP, need to estimate Project modification, Exposure creation and Provider adding to the directory screens part of Admin flow estimation with minimal requirement to make a meaningful Admin workflow even though it listed as different sessions in Figma prototype . Exposure screen full implementation will be taking care part of My Projects/Community module estimation/implementation
6 | Deaglo Admin-> View Trades functionality can be implemented at later stage after the Community & My Projects main flow implementation since there is a dependency
7
8
9
10

## Estimation Sheet
|  |  | Requirement- 10% |  |  |  | Design - 15% |  |  | Coding - 45% | [6 empty] | Testing - 25% |  |  |  |  | Release - 5% |  |  | Total (Hrs)
Sl.No | Screens | Complexity | Requirement Gathering | SRS Preparation | SRS Review | SRS Rework | Technical Design Specifications | TDD Review | TDD Rework | View | Business Layer | DAO Layer | Unit Testing | Rework after Unit Testing | Code review | Code Rework | STP / STD Preparation | STD / STP Review & Rework | Functional Testing | Automation Testing | Rework on Testing Comments | Deployment | User Manual | System testing & UAT Support | Total (Hrs) | Total (Days)
User Entry Columns |  |  | Formula Columns
1
2
<Function Name>
1
2
3
4
5
<Function Name>
1
2
3
7
4
5
6
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100

## Project Cost
Resource | Hrs/Month | Months Reqd. | Billing Rate/Hr | Cost
PM | 160 | 4.5 | 26 | 18720
FE | 160 | 4.5 | 26 | 18720
BE | 160 | 4.5 | 26 | 18720
QA | 160 | 3.25 | 24 | 12480
|  |  | Total Cost | 68640

## Gantt Chart
Modules/Milestones | Start Date | End Date | Days To Complete(Calender Days)
Python Fun Modifications & Deployment | 2022-04-20 | 2022-05-03 | 13
New Dev Environment Setup | 2022-04-20 | 2022-05-10 | 20
Create/Universal Functionalities | 2022-05-10 | 2022-06-07 | 28
Client Admin Functionalities | 2022-06-07 | 2022-07-19 | 42
Deglo Admin Functionalities | 2022-07-19 | 2022-08-23 | 35

## User Stories
Python Function Modifications & Deployment:
------------------------------
1) As a developer, I would like to fetch Forward data details from Bloomberg with minimum universe setup & write deaglo specific logic
2) As a developer, I would like to fetch Volatility data details from Bloomberg with minimum universe setup & write deaglo specific logic
Environment Setup:
--------------------
1) As a developer, I need a new AWS develop environment for backend activities by mirroring the MVP1 backend environemnt
Create/Universal Functionalities :
------------------------------
1) As a user, I would like to create the project by selecting Base currency and see a chart default to last run simulation or a spot history chart that defaults to the base currency against a standard hard coded currency,EUR.
2) As a user, I would like to create an organization corresponding to a project and organization has one to one mapping with project
3) As a user, I would like to create an exposure for a project by selecting Term currency and other inputs
4) As a user, I would like to see a drop down for Exposure Category selection and it should list "Foreign share class","Foreign investment","Operational fx"
5) As a Project owner, I would like to add new providers to Provider directory by selecting Provider name, email, person name and trigger an email invite
6) As a Project owner, I would like to see an option selector(:) on the right top against each providers with following options "Edit Provider Info","Remove from directory"
7) As Project owner, I would like to remove providers from Provider directory by selecting "Remove from directory" option
8) As a Provider,I would like to get an email alert with platform link whenever user/admin tries to add part of analysis and I should be able to redirect to platform login screen by clicking the link
9) As a Provider,I would like to sign up/ sign in to platform by providing the details and should able to see the request in Notification
10) As a Provider,I would like to Approve/Reject request to become part of analysis from Notification
Client Admin Functionalities:
-------------
1) As a Client Admin,I would like to select providers to the team by clicking "Provider" button and select from directory
2) As a Client Admin,I would like to remove providers from the team by selecting "Remove Provider" option
3) As a Client Admin,I would like to add member to the team by clicking "Member" button. Provide Email,Company Name to initiate the email invite
4) As a Client Admin, I would like to see an option selector(...) on the right side against each member with following options "Change Role","View Profile", "Remove from Organization"
5) As a Client Admin,I would like to remove member from organization by selecting "Remove from Organization"
6) As a Client Admin,I would like to set a specific role for member by selecting appropriate role from the drop down options. Dropdown should have these roles "Admin", "Member" and "Viewer"
7) As a user, I would like to create a request to join an organization and this triggers a notification to the org owner and admin, who can decide to accept the requester where it generates an invite email and notification as the user is an existing user
8) As a Project owner, I would like to get an email alert whenever an organization joning request takes place and also I should be able to see the request in notification list
9) As a Project owner, I would like to Approve/Reject organization joning request from notification
Deaglo Admin Functionalities:
-------------
1) As a Deaglo Admin, I would like to see a menu called "Deaglo Admin" in the left pannel as soon as I got logged in
2) As a Deaglo Admin, I would like to see all the platform users listed in a grid view up on "Deaglo Admin" menu click and it should display users details such as User Name,Member Type,Sub. End Date and Last Logged
3) As a Deaglo Admin, I would like to see all the platform users listed in a grid view up on "Deaglo Admin" menu click and user details should be able to Export as csv file
4) As a Deaglo Admin, I would like to see an option selector(...) on the right side against each user with following options "View profile","Freeze Account", "Trigger Password Reset" and "Delete User"
5) As a Deaglo Admin, I would like to navigate to users profile up on "View Profile" click and should be able to view the project details and exposure details associated with that selected users
6) As a Deaglo Admin, I would like to navigate to users profile and should be able to Export the selected exposure screen as pdf
7) As a Deaglo Admin, I would like to Freeze/InActive a user account by selectng the option "Freeze Account" and disable user to log in to the platform
8) As a Deaglo Admin, I would like to Reset Password for a user account by selectng the option "Trigger Password Reset" and should trigger an email to the user
9) As a Deaglo Admin, I would like to soft Delete a user account by selectng the option "Delete User" and disable user to log in to the platform
10) As a Deaglo Admin, I would like to Invite a user by sending an email invitation up on "Invite User" button click and by providing an email address
11) As a User, I would like to get an email alert with platform link whenever Admin tries to add a user to the platform and I should be able to redirect to platform login screen by clicking the link
12) As a User, I would like to sign up/ sign in to platform by providing the details and should able to see the request in Notification
13) As a Deaglo Admin, I would like to click "Organization" button and should be able to view the details
14) As a Deaglo Admin, I would like to click "View Trades" button and should be able to view the details
Assumptions:
___________
1) Community & My Projects dependent functionalities which are essential to implement Admin func. only considered for now(refer the user stories listed above under Universal/Creation section) and all other left out functionalities will do later with separate estimation.
2) Deaglo Admin-> View Trades functionality can be implemented only after the Community & My Projects main flow implementation since there is a dependency.

## Project Plan (hidden)
Sl.No | Task | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21
1 | Requirement & Planning
1.1 | Training & Environment setup
1.1.1 | High Level Business walkthrough
1.1.2 | Customer Application Training
1.1.3 | Software Installation
1.1.4 | Application and Database setup
1.1.5 | ….
Software Licenses
Milestone - Completion of Project Environment Setup`
1.2 | Requirement Gathering and Analysis
1.2.1 | Gather and analyze the requirement
1.2.2 | Understanding of Application Database and related environment
1.2.3 | ….
Dependency - NFR Requirement from Customer
Milestone - Capture Non-functional requirements
1.3 | Scope & Planning
1.3.1 | Scope Document
1.3.2 | High Level Plan
1.3.3 | Estimation
1.3.4 | Design Approach
1.3.5 | RACI Matrix
1.3.6 | ….
Dependency - Review and Approval of Scope & Planning Documents
Milestone - Delivery of Scope Document, High Level Plan, Estimation, Design Approach & RACI Matrix
2 | Design, Build & Solution Testing
2.1 | Solution Design
2.1.1 | Design Task
2.1.2 | …
2.1.2
2.1.3
2.2 | Solution Coding & UnitTesting
2.2.1 | Coding related task
2.2.2 | …
Dependency - Sample Test Data from CPP for all entities
2.2.3 | xxx
2.2.4 | xxx
2.2.5 | Unit Testing
2.2.6 | Review & Rework
Milestone - Code built and unit tested
Dependency - Review and Approval of Code
3 | Functional Testing
3.1 | Functional Testing
Dependency - Built and delivery of Applcation
Dependency - Test Data for System Testing
3.1.1 | Setup test data
3.1.2 | Automated Regression testing of Application to make sure all the pages are loading properly and there are no functional issues
3.1.3 | Fix the testing issues & Share the test results
Milestone - System Testing Complete
Dependency - Review and Approval of Test Report
4 | System Testing
4.1 | System Testing
Dependency - Built and delivery of Applcation
Dependency - Test Data for System Testing
4.1.1 | Setup system test data
4.1.2 | xxx
4.1.3 | ….
Re-Testing & Defect Clearnace
Milestone - Data Quality Testing Phase 1 Complete
4 | UAT Support
5.1 | User Acceptance Testing
5.1.1 | Support for UAT
5.1.2 | Defect clearance
Milestone - Parallel Testing / Live Proving Complete
Depedency - UAT Sign-off
6 | Go Live, Maintenance & Support
6.1 | Go Live
6.1.1 | Deployment procedure
6.1.2 | Live Environment setup
6.1.3 | Live Deployment
Milestone - Go Live
6.2 | Maintenance & Support
Sample Project Plan - Detailed

## High Level plan (hidden)
Different Phase of Project | Duration (Months) | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21
Program & Project Management | 3 | M1: Program & Project Management
Requirement & Planning | 2 | M1: Requirment & Planning
Design, Build & Solution Testing | 4 | M3: Design, Build and Unit Testing
Functional Testing |  | M7: Functional Testing
System Testing |  | M11: System Testing
UAT Support |  | M15: UAT Support
Parallel Testing / Live Proving |  | M18: Live Test
Go Live |  | M19: Go Live
Support and Maintenance |  | M19: Maintenance and Support
Defect Clearance |  | M11: Defect Clearance
Sample - High Level Plan

## Resource Loading (hidden)
Duration | Different Phase of Project |  | 2014-10-01 | 2014-11-01 | 2014-12-01 | 2015-01-01 | 2015-02-01 | 2015-03-01 | 2015-04-01 | 2015-05-01 | 2015-06-01 | 2015-07-01 | 2015-08-01 | 2015-09-01 | 2015-10-01 | 2015-11-01 | 2015-12-01 | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01
1-19 | Project Management |  | 2014-10-01: Program & Project Management
1-2 | Requirement & Planning |  | 2014-10-01: Requirment & Planning
3-6 | Design, Build & Solution Testing |  | 2014-12-01: Design, Build and Unit Testing
7-10 | Integration Testing |  | 2015-04-01: Integration Testing
10-13 | System Testing |  | 2015-08-01: System Testing
14-17 | UAT Support |  | 2015-12-01: UAT Support
18 | Live Test Support |  | 2016-03-01: Live Test
19 | Go Live Support |  | 2016-04-01: Go Live
19-21 | Support and Maintenance |  | 2016-04-01: Maintenance and Support
7-18 | Defect Clearance |  | 2015-08-01: Defect Clearance
|  |  | 106 |  | 680 |  |  |  |  | 406 |  |  | 415 |  |  |  | 223 |  |  | 145
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
Sl.No | Role / Month | Total | 2014-10-01 | 2014-11-01 | 2014-12-01 | 2015-01-01 | 2015-02-01 | 2015-03-01 | 2015-04-01 | 2015-05-01 | 2015-06-01 | 2015-07-01 | 2015-08-01 | 2015-09-01 | 2015-10-01 | 2015-11-01 | 2015-12-01 | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01
1 | Program Manager (Onsite) | 241 | 11 | 20 | 18 | 18 | 18 | 18 | 18 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 371
2 | Project Manager (Offshore) | 125 | 5 | 10 | 10 | 10 | 10 | 10 | 10 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
3 | Business Analyst | 5 | 106 2: 5
4 | Migration Consultant (Tech Arch) | 63 |  | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 2 | 5 | 2 | 2 | 2 | 5 | 2 | 2 | 2 | 5 | 2 | 1196
5 | Technical Lead (Onsite) | 331 | 5 | 20 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
6 | Technical Lead (Offshore) | 331 | 5 | 20 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18
7 | Offshore Sr.Developer 1 | 214 |  |  | 6 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 10
8 | Offshore Sr.Developer 2 | 119 | 680 5: 18; 680 6: 19; 680 7: 18; 406 8: 18; 406 9: 18; 406 10: 18; 415 11: 10
| Offshore Sr.Developer 3 |  | 680 5: 18; 680 6: 19; 680 7: 18
9 | Offshore Sr.Developer 4 | 83 | 680 5: 18; 680 6: 19; 680 7: 18; 406 8: 18; 406 9: 10
10 | Offshore Test Lead | 262 |  |  |  |  | 10 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 408
11 | Offshore Sr.Test Engineer | 146 | 680 5: 10; 680 6: 18; 680 7: 18; 406 8: 18; 406 9: 18; 406 10: 18; 415 11: 18; 415 12: 18; 415 13: 10
| Total | 1920 | 26 | 80 | 75 | 87 | 161 | 180 | 177 | 143 | 135 | 128 | 117 | 107 | 99 | 92 | 81 | 71 | 71 | 74 | 71
Sl.No | Effort / Month wise | Total | 2014-10-01 | 2014-11-01 | 2014-12-01 | 2015-01-01 | 2015-02-01 | 2015-03-01 | 2015-04-01 | 2015-05-01 | 2015-06-01 | 2015-07-01 | 2015-08-01 | 2015-09-01 | 2015-10-01 | 2015-11-01 | 2015-12-01 | 2016-01-01 | 2016-02-01 | 2016-03-01 | 2016-04-01
62.29% | Developer Effort | 1196 | 10 | 45 | 47 | 59 | 113 | 116 | 113 | 92 | 84 | 77 | 66 | 56 | 56 | 59 | 48 | 38 | 38 | 41 | 38
21.25% | Testing Effort | 408 | 0 | 0 | 0 | 0 | 20 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 28 | 18 | 18 | 18 | 18 | 18 | 18
19.32% | Program Mgmt + Project Mgmt | 371 | 16 | 35 | 28 | 28 | 28 | 28 | 28 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
| Total | 1975 | 26 | 80 | 75 | 87 | 161 | 180 | 177 | 143 | 135 | 128 | 117 | 107 | 99 | 92 | 81 | 71 | 71 | 74 | 71
| Effort / Phase wise |  | 106 1: Requirment & Planning; 680 3: Desing, Build and Unit/Reconcile Testing; 406 8: Integration Testing; 415 11: System Testing; 223 15: UAT Support; 145 18: Go Live
62.29% | Developer Effort | 1196 | 106 1: 55; 680 3: 448; 406 8: 253; 415 11: 237; 223 15: 124; 145 18: 79
21.25% | Testing Effort | 408 | 106 1: 0; 680 3: 92; 406 8: 108; 415 11: 118; 223 15: 54; 145 18: 36
19.32% | Program Mgmt + Project Mgmt | 371 | 106 1: 51; 680 3: 140; 406 8: 45; 415 11: 60; 223 15: 45; 145 18: 30
| Total | 1975 | 106 | 0 | 680 | 0 | 0 | 0 | 0 | 406 | 0 | 0 | 415 | 0 | 0 | 0 | 223 | 0 | 0 | 145
Note on F23: Training Effort is not included

## Schedule (hidden)
Project Schedule
Task Name |  | Estimated Effort (Days) | Planned Start | Planned Finish | Actual Start | Actual End | Actual Effort | Resource Initials | Lead 1 | Lead 2 | Sr.Dev1 | Sr.Dev2 | Sr.Dev3 | Sr.Dev4
Project Environment Setup | Estimation (Hrs) | 0 | 2015-03-02 | 2015-03-12 |  |  |  | All | 11 | 10 | 1 | 1 | 1 | 1
Installation of Softwares (Eclipse, WAS, DB2) | 40 |  | 2015-02-02 | 2015-02-03 |  |  |  | All | [6 empty] | Lead 1 | 90 | 11.25 | Onsite Lead | Lead 1
Setting up Staging DB | 24 |  | 2015-02-04 | 2015-02-06 |  |  |  | Lead1 | [6 empty] | Lead 2 | 83 | 10.375 | Offshore Lead | Lead 2
SVN codebase setup | 8 |  | 2015-02-03 | 2015-02-03 |  |  |  | All | [6 empty] | Sr.Dev1 | 10 | 1.25 | Senior Developer 1 | Sr.Dev1
Solution Proving - POC | 84.8 |  | 2015-02-09 | 2014-02-13 |  |  |  | Lead1 & Lead2 | [6 empty] | Sr.Dev2 | 10 | 1.25 | Senior Developer 2 | Sr.Dev2
Setting up Development Server (Continous Build and Integration) | 40 |  | 2015-02-17 | 2015-02-21 |  |  |  | Lead2 | [6 empty] | Sr.Dev3 | 10 | 1.25 | Senior Developer 3 | Sr.Dev3
Setting up Testing Server (Testing Database and WAS) | 24 |  | 2015-03-10 | 2015-03-12 |  |  |  | Lead1 | [6 empty] | Sr.Dev4 | 10 | 1.25 | Senior Developer 4 | Sr.Dev4
Framework Creation |  | 50.05 | 2015-02-01 | 2015-02-01 |  |  |  | All | 10 | 10 | 12 | 5 | 5 | 5
Project Structure definition(Modularising) | 42 | 5.25 | 2015-02-02 | 2015-02-04 |  |  |  | Lead1, Lead2
xxx | 56 | 7 | 2015-02-16 | 2015-02-19 |  |  |  | Lead1, Lead2
xxx | 0
xxx | 33.6 | 4.2 | 2015-02-04 | 2015-02-09 |  |  |  | Sr.Dev2 | [6 empty] | Lead 1 | 80 | 10
xxx | 33.6 | 4.2 | 2015-02-04 | 2015-02-09 |  |  |  | Sr.Dev3 | [6 empty] | Lead 2 | 80 | 10
xxx | 33.6 | 4.2 | 2015-02-04 | 2015-02-09 |  |  |  | Sr.Dev4 | [6 empty] | Sr.Dev1 | 96 | 12
xxx | 44.8 | 5.6 | 2015-02-10 | 2015-02-13 |  |  |  | Sr.Dev3, Sr.Dev4 | [6 empty] | Sr.Dev2 | 40 | 5
xxx | 0 | [13 empty] | Sr.Dev3 | 40 | 5
xxx | 33.6 | 4.2 | 2015-02-19 | 2015-02-24 |  |  |  | Lead1, Lead2 | [6 empty] | Sr.Dev4 | 40 | 5
xxx | 33.6 | 4.2 | 2015-02-25 | 2015-03-03 |  |  |  | Lead1, Lead2
xxx | 11.2 | 1.4 | 2015-02-27 | 2015-02-27 |  |  |  | Lead2
Exception Handling | 33.6 | 4.2 | 2015-02-10 | 2015-02-13 |  |  |  | Sr.Dev1, Sr.Dev2
Error logging | 44.8 | 5.6 | 2015-02-16 | 2015-02-23 |  |  |  | Sr.Dev1
Milestone : Framework Development Complete |  |  |  | 2015-03-06
Develop - Contacts Module |  | 28.4 | 2015-02-01 | 2015-03-01 |  |  |  | Arch, Lead1, Lead2, Sr.Dev1, Sr.Dev2 | 8 | 8 | 14 | 22
xxx
xxx | 72 | 9 | 2015-02-17 | 2015-02-27 |  |  |  | Lead1, Lead2, Sr.Dev2 | [6 empty] | Lead1 | 66 | 8.25
xxx | 72 | 9 | 2015-02-23 | 2015-02-28 |  |  |  | Lead1, Lead2, Sr.Dev1 | [6 empty] | Lead2 | 65 | 8.125
Unit Testing | 22.4 | 2.8 | 2015-03-13 | 2015-03-17 |  |  |  | Lead1, Lead2, Sr.Dev1, Sr.Dev2
Error Handling | 60.8 | 7.6 | 2015-03-12 | 2015-03-17 |  |  |  | Lead1, Lead2, Sr.Dev1, Sr.Dev2
Milestone : Contacts Module Development Complete |  |  |  | 2015-03-31
Develop - Admin Module |  | 23.4 | 2015-02-01 | 2015-03-01 |  |  |  | Arch, Lead1, Lead2, Sr.Dev3, Sr.Dev 4 | 8 | 8 |  |  | 20 | 22
xxx
xxx | 92.8 | 11.6 | 2015-02-17 | 2015-02-27 |  |  |  | Lead1, Lead2, Sr.Dev3
Unit Testing | 33.6 | 4.2 | 2015-03-12 | 2015-03-17 |  |  |  | Lead1, Lead2, Sr.Dev3, Sr.Dev4
Error Handling | 60.8 | 7.6 | 2015-03-14 | 2015-03-19 |  |  |  | Lead1, Lead2, Sr.Dev3, Sr.Dev4
Milestone : Admin Module Development Complete |  |  |  | 2015-04-17
Note on S5: POC - 42 Test Server - 24 Stage DB -24
Note on S6: POC - 42 Dev Server - 40
Note on S7: Installation - 8 SVN - 2
Note on S8: Installation - 8 SVN - 2
Note on S9: Installation - 8 SVN - 2
Note on S10: Installation - 8 SVN - 2
Sample - Project Plan

## Template log (hidden)
Document Name: |  | Aspire- SMC -Estimation -template
Document ID: |  | Aspire- SMC -Estimation -template
Version: |  | 1.1
Date: |  | February 15,2022
Modification History
(Kindly remove the modification history of the Template when using this sheet)
Purpose of the Template |  | This template can be used when SMC Estimation
Date | Author |  | Change Description | Version
April 16, 2015 | Nirmalraj Suriyakaanthan |  | Ceated | 0.1
May 11, 2015 | Nirmalraj Suriyakaanthan |  | Modified | 0.2
2015-08-04 | Nirmalraj Suriyakaanthan |  | Updated the estimation sheet to autopopluate the values based on the complexity selection | 0.3
February 28,2019 | Anandha Duraipandi |  | Reviewed and changed logo & copyrights info | 1.1
February 26,2020 | SEPG |  | No review comments and approved | 1.1
February 26,2021 | SEPG |  | Reviewed and no changes | 1.1
February 15,2022 | Sahaya Joni |  | Reviewed and no changes | 1.1